GOODProjects

Action Plan: Everything Still Needed

CAH FY27 Field Trip Experiences Grant, deadline 5:00 PM ET, Thursday, July 24, 2026

Purpose: a single, ordered to-do list covering every outstanding requirement across the RFA and

the Addendum A work samples/support materials/résumés rules, so nothing gets requested at the

last minute. Organized by who needs to act, not by document type, so this can be split up and

sent out today.

## PRIORITY 1: WORK SAMPLES (highest-weighted content item, request TODAY)

Addendum A confirms work samples carry the most weight of any content item and must be no more

than 3 years old. GOODProjects has not yet run this exact field trip, but the RFA explicitly

allows "samples of similar projects completed to illustrate an ability to execute the proposed

project." That means we don't need Arena Stage-specific footage; we need real documentation of

GOODProjects successfully running arts-based or dance-based youth programming.

Real candidates already likely to exist, ranked by fit:

GOODSports dance sessions: GOODSports explicitly includes dance as a life-skills vehicle.

This is the closest match to this application's Dance discipline classification.

Christmas Play (Dec 16, on the 2026 community calendar): an actual GOODProjects-produced

performing arts event. Strong general arts-programming evidence even outside the Dance

discipline label.

Family Arts & Craft Festival (May 1, on the 2026 community calendar): a real, named

GOODProjects arts event; useful if photo/video documentation exists.

STREAM programming (the "Arts" component specifically): worth checking for any

documented sessions.

Action: ask Adam Hickson (Communications Lead: he owns photo/video/social content) today

whether usable photo or video documentation exists from any of the above, dated within the last 3

years. If video, confirm it's not a highly-edited promotional piece (Addendum A explicitly says

not to submit those) and that it's under 5 minutes, or has a marked timecode if longer.

Technical specs to hold every sample to, per Addendum A:

Photos: JPEG/JPG, minimum 72 dpi, max 8MB each

Video: no highly-edited/promotional footage; no dim lighting, shaky video, or backlighting; if

over 5 minutes, mark the exact timecode panelists should start at

Audio: panelists cannot skip or rewind, so any clip must be pre-edited to the exact content

wanted; if there's a visual element, submit as video instead

Every sample must be labeled with a specific name and title so panelists know what they're

looking at

A website screenshot is not an adequate substitute for a real work sample; panelists do not

click outside links

Do not over-submit: Addendum A explicitly warns that adding more samples than needed weakens

an application, not strengthens it. Pick a small number of the strongest, most relevant items.

## PRIORITY 2: SUPPORT MATERIALS (up to 3 items, request THIS WEEK)

Best real option: a letter of support from Jefferson Middle School. GOODLearningHub already

partners with Jefferson Middle School (Jefferson Academy): the 6th-8th grade participants for

this trip would specifically be GOODLearningHub students attending Jefferson during the day. A

letter from a Jefferson administrator or teacher would also directly support the RFA's own goal

of "collaboration with appropriate personnel at DCPS/DCPCS."

Action: ask Stephanie Page-Baxter (she oversees the Jefferson Middle School partnership) to

request a short letter of support this week: this kind of ask can take longer than expected to

get signed off by a school administrator, so it shouldn't wait.

Other eligible support material types (need at most 2-3 total, don't overload):

Sample syllabi/lesson plans: this one we can draft ourselves rather than wait on anyone (see

Priority 3 below, since it overlaps with Arts Merit evidence)

Any theater/exhibition reviews, certificates, or awards tied to prior arts programming, if they

exist and are genuinely relevant (not a general org award like Darius's Forbes 30 Under 30,

which isn't arts-specific and would weaken rather than strengthen this particular category)

## PRIORITY 3: RÉSUMÉS OF KEY PERSONNEL (needs direct outreach, request THIS WEEK)

The RFA requires each résumé to include role, area of responsibility, AND ward or state of

residence: this last detail isn't in any org profile document and has to come directly from each

person.

Action: request current résumés plus ward/state of residence directly from:

Stephanie Page-Baxter (Director of Youth Development: designs the curriculum connections;

her 34 years as a DCPS educator and Hampton/GWU degrees are strong, relevant credentials)

Phileke Holland (Afterschool Coordinator: leads day-to-day facilitation)

If Arena Stage's teaching artists will be named individually in the application, ask Arena Stage's

Group Sales/education contact whether they can provide a short bio for the specific artist(s)

assigned: this may not be available until closer to the actual performance date, so flag it as

lower urgency but still worth asking now.

## PRIORITY 4: EVALUATION DESIGN (small fix, do this week)

Addendum A distinguishes qualitative (narrative, subjective) from quantitative (empirical,

measurable) assessment and expects applicants to think about both. Our current evaluation metrics

(attendance percentage, survey completion percentage, staff PD completion) are entirely

quantitative. Adding one qualitative element, such as a short written or verbal reflection

prompt captured from a sample of students post-trip, would round this out and directly answers

what Addendum A is asking for. This is a five-minute addition to the narrative, not a new

workstream.

## PRIORITY 5: COMPLIANCE DOCUMENTS (route to Cole Bradshaw now, several need real lead time)

These were already flagged in the attachments checklist but are repeated here because a few of

them cannot be produced same-day:

| Document | Status | Why it needs lead time |
| --- | --- | --- |
| Certificate of Liability Insurance (with waiver of subrogation) | Unknown if on file | Obtaining or amending a policy can take days to weeks |
| Current Organizational Budget | Must be Board-approved | If not already approved, needs a Board sign-off, not just a staff draft |
| Certificate of Clean Hands | On file but dated 4/23/2026, likely stale | RFA requires issuance within 30 days of the deadline; reissuing through MyTax DC isn't instant |
| Business License / DLCP registration | Status unknown | This is a baseline eligibility requirement, not just an attachment; confirm now, not the week of the 24th |
| Balance Sheet, Form 990, P&L Statement | Not yet sourced | Straightforward to pull, but still needs someone to actually pull them |
| Board of Directors list with roles, responsibilities, and home addresses/wards | Exists without ward/address detail | Needs augmenting, likely requires reaching out to individual board members |
| Signed IRS W-9 (March 2024 version specifically) | Not yet confirmed current | Must be dated to match the actual submission date and address must match the grants portal and DIFS exactly |
| Statement of Certification | Not yet done | Can't be completed until a submission date is set, but shouldn't be the last thing done the night of the 24th |
| Financial misconduct/fraud disclosure statement | Not yet drafted | A short sworn statement; simple to write once someone owns it |
| CAH Budget Form (their own template) | Not yet sourced | Needs to be pulled from the Submittable portal directly |

Action: send this table to Cole Bradshaw today. He already owns Clean Hands, business

licensing, and financial documentation per GOODProjects' own staff records, so he's the right

first stop for nearly all of it.

## STILL WAITING ON NEO (from the separate Questions for Neo document)

Not repeated in full here, but flagging that Priority 1-3 above shouldn't start until Neo has

confirmed the grade band (6th-8th, Dance) and whether this is a weekday or weekend matinee, since

that affects which students, which school partner, and which letter of support actually make

sense to request.

GOODProjects, Inc. | 996 Maine Avenue SW, Suite 208, Washington, DC 20024 | EIN 81-1491594 | grants@goodprojects.org