GOODProjects

Submission Readiness Summary

CAH FY27 Field Trip Experiences Grant, deadline 5:00 PM ET, Thursday, July 24, 2026

This is a plain answer to "is this ready to submit": not yet, and it cannot be made fully ready

by drafting alone. Everything below is sorted into what's actually finished versus what

structurally requires a real person to act, sign, call, or confirm something I have no way to

verify or produce myself.

## DONE: fully drafted, ready to use or send as-is

Full grant narrative (13 sections), rebuilt around the real, verified plan: Step Afrika! at

Arena Stage, 6th-8th grade, Dance discipline

Corrected, itemized $5,500 budget with real Arena Stage pricing, cost-cap compliance checked

against the RFA's 35%/25% limits

Confirmed funder cap ($30,000), confirmed deadline (5:00 PM ET, July 24), confirmed Program

Officer contact (Andrea Brown), confirmed submission channel (Submittable)

Full eligibility check against the RFA's 8 minimum requirements and exclusion list

Pre-trip workshop lesson plan and post-trip reflection activity, fully written with objectives,

sequencing, and curriculum alignment

Facilitator bios for Stephanie Page-Baxter and Phileke Holland, built from verified real facts

Qualitative evaluation component added, closing the Addendum A gap

Statement of Certification and financial misconduct disclosure, drafted as templates

Ready-to-send outreach messages for every person whose input is still needed

A prioritized action plan and a separate questions-for-Neo document

All em and en dashes removed across every document

Every document exported to Word and pushed to the repository

## CANNOT BE COMPLETED WITHOUT A REAL PERSON, no matter how much I draft

These aren't oversights; they are things that structurally require a human, an institution, or a

signature, and no amount of additional drafting changes that:

Neo's approval of the grade band, the weekday-vs-weekend matinee decision, and the $5,500

budget. Nothing below should proceed until this happens.

A phone call or email to Arena Stage to confirm the actual matinee date and get a real

ticket quote. I drafted the script; someone has to place the call.

Real photo or video work samples from GOODProjects' own past events. I cannot generate or

fabricate these; they exist only in Adam Hickson's files, if they exist at all.

Each facilitator's ward or state of residence, a personal detail only Stephanie and Phileke

can provide.

A letter of support from Jefferson Middle School, which requires a real administrator's

time and signature.

GOODLearningHub's actual 6th-8th grade headcount, a real enrollment number only Stephanie

or Phileke can pull.

Every compliance document Cole Bradshaw owns: Clean Hands reissuance, Business

License/DLCP confirmation, signed W-9, liability insurance certificate, Board-approved

organizational budget, Form 990, balance sheet, P&L statement, and an updated Board list with

ward/address detail. None of these can be produced by drafting; they require real financial

records, a real insurance policy, and in one case a real Board vote.

**Confirmation of whether GOODProjects applied for CAH's FY27 General Operating Support

grant.** Only Neo can answer this, and it could affect eligibility outright.

Darius Baxter's actual signature on the Statement of Certification and the financial

misconduct disclosure, the latter also requiring his factual confirmation, not mine.

A CAH technical assistance appointment, if you want one, must be booked by a person before

Friday, July 17.

A Submittable account and the actual submission itself, which requires portal access and

someone with the authority to hit submit.

## THE HONEST BOTTOM LINE

I've closed every gap that was mine to close: the narrative is strong, accurate, and internally

consistent; every template a human needs to act on is drafted and ready to send; every remaining

gap is labeled with exactly who needs to do what. But "ready for submission" in the sense of

"could go out the door today" isn't achievable without Neo's sign-off and roughly a dozen pieces

of real-world action from Neo, Stephanie, Phileke, Cole, Arena Stage, and Darius. That's not a

shortfall in the work, it's what CAH's own process actually requires of any applicant.

GOODProjects, Inc. | 996 Maine Avenue SW, Suite 208, Washington, DC 20024 | EIN 81-1491594 | grants@goodprojects.org